## Introduction
Synthetic Sports Surfaces Self‑Assessment Checklists
Purpose
These checklists support the planning of synthetic sports surface projects by providing a structured set of considerations across planning, design, procurement and management.
They are intended to:
  Support consistent and evidence-based decision-making
  Identify key risks early, particularly around demand, cost and maintenance
  Assist in documenting how decisions have been assessed and justified
How to use
The checklists are a self-assessment tool to be used throughout project development.
They should be:
  Completed progressively as the project develops
  Used to inform discussions across planning, asset, design and operations teams
  Supported by evidence, including demand analysis, site assessments and strategic alignment
  Reviewed at key points such as project initiation and business case development
The structure reflects a lifecycle approach:
  Planning – demand, need and site suitability
  Design – performance standards and whole-of-life considerations
  Procurement – delivery approach and quality control
  Management – maintenance, programming and replacement
Important
These checklists are not standalone and must be used in conjunction with the full guidelines as they provide the detailed context, technical requirements and supporting evidence needed to properly assess each item. The checklists summarise key questions only and do not replace detailed analysis.
Key considerations
Users should ensure that:
  Demand is clearly demonstrated and aligned to provision
  Whole-of-life costs are understood, including renewal
  Maintenance requirements are defined and resourced
  Stakeholder engagement has been undertaken
  Proposals align with relevant strategies and policies
  Failure to address these areas at the planning stage increases the risk of poor investment outcomes, higher long-term costs and reduced asset performance.
Disclaimer
These checklists are provided to support the planning and assessment of synthetic sports surface projects. They are guidance only and are intended to assist structured, evidence-based decision-making.
They summarise key considerations and do not replace detailed technical, financial or environmental assessment. They must be used in conjunction with the full Planning Guidelines for Decision Makers and associated technical guides.
Users are responsible for undertaking appropriate investigations, stakeholder engagement and approvals in line with their organisation’s requirements and applicable legislation.
This material has been developed with input from multiple parties. While reasonable care has been taken, no party involved in its preparation accepts liability for any loss or damage arising from reliance on its contents.
This document is not a controlled document once downloaded or printed. Users must ensure they are using the current version.

## Planning
Sports Surface Component Considerations | Benchmarked Solution and Preferences | Self-assessment Result
1. PLANNING
Scope of Brief Confirmation
Clarity of Brief | Is there clarity on the scope of the brief to ensure it meets the criteria and benefits of the broader community.
Needs Assessment
Catchment area identification | Has a need been established within the local government area and has this been agreed by the sport e.g. State Sports Association (SSA), local Council &/or state government.
Existing facilities audit | Has local facilities in the area been audited by council, the sport or other organisations to demonstrate specific needs for this request. This may include Regional Associations, SSA or NSO facility audits/ state strategies or local council recreation policies etc.
Demographic analysis for current and future growth needs | Does the local demographic profile align with the facility request and programming ability. The demographic analysis should be able to justify any gaps between the needs and wants of the project.
Participation data collected to determine needs | Have you embraced demographic data currently and for the future (25 years plus) this should allow for the collection of information on population density, age and gender structure, income and household profiles, and ethnicity. Expectations for growth or demographic changes are needed.
Alignment of sport and recreational needs analysis | Does the local participation data provide the supply and demand modelling to justify the needs of any future facility.
Does the demand justify the level of provision, whether that be local, district, regional, state or national level. This data should provide the reality, not the aspiration of needs.
Stakeholder alignment | Has stakeholder and community consultation been conducted to support the project in an open and transparent manner.
Conversion from natural to synthetic or hybrid surfaces | Has the social trade-off of reducing natural turf been assessed? (i.e. if the site was used casually for play, social sport, picnics etc. and it is converted to synthetic and also therefore potentially fenced off, has the loss of natural turf been considered? (I.e. not just getting councils to assess the needs and demands, but the reverse loss in not being able to use it for more social/recreational purposes?)
Provision Assessment
Site assessment | Justification that the current site cannot accommodate the current or future demand without such technological improvements.
A council/regional-wide geographical assessment should consider which is the best site to encourage broad community usage.
Number of synthetic fields of play in the area and how does the proposed one complement others and are part of a network solution to address capacity issues in the area.
Exploration of other options (e.g. natural surface upgrade with drainage & irrigation system improvements or use of hybrid technology).
Exploration of flooding, bushfire, environmentally or residentially sensitive areas prior to the agreement of the site.
Supply and demand identify needs and gaps | There is a need to quantify current and future needs for participants and this will allow clarity on the surface type needed.
Sports Provision & Capacity | Complete a demand assessment analysis, agreed with the Sports SSA, to justify the need for new facilities and/or upgrade existing ones. This should consider recreational needs, training, and competition needs.
Community & stakeholder consultation | Community consultation at an early stage to reflect the whole community, including all (potential) users, key stakeholders, and the community who may be impacted by the development potentially from increased usage, traffic, noise, or lights.
Policy & Strategy Alignment
Organisational alignment | Does the project consider the open space, recreation needs, and sporting facilities strategies as well as the SSA needs studies.
External alignment of policy and strategies | Consult and confirm any strategic needs and how this planning request will fit into state/territory, commonwealth, and local government strategies, both within this location and the neighbouring ones.
Approved masterplan | Is there a masterplan or identified need by council for the facility as this site that has been agreed by council that you can align to.
Sports Specific Needs
Aspirations | How does the organisations aspirations align with the demographic and sporting needs for the future.
Specific technical needs for surface | Certain sports have requirements for the surface types and performance criteria and most are linked to the level of play, from multi-sport to training, community, regional, state, national, and international; play requirements.
Work with local SSA to identify the actual standards and type of surface needed for the field of play, not just the aspirational needs
Surface type | A decision should be made that clearly justifies why a specific surface type is decided upon, whether that be natural grass, synthetic or hybrid grass, acrylic surface, rubber track or specialist surfaces for each sport (e.g. woven carpet for bowls etc)
Sport specified surface | Does the sport specify a specific type of surface, such as Hockey, Athletics, Netball etc that means it will not be played on natural grass
Management Considerations for Future Proofing
Site management Strategies | Has the owner of the facilities (e.g. local council) agreed how the site should be managed (e.g. lease, license, Council management etc) and will this impact the management of the proposed facility.
Maintenance responsibilities and strategies | Is there an agreement (MoU/Lease agreement etc) that clearly identifies the maintenance, repair, restoration and replacement of the surfaces being requested.
Usage levels | Is there clearly modelled (& conservative) projected usage of the proposed surface and will that surface be able to cope with the demand modelling.
Standards of play | Are the standards of surface clearly defined, fit for purpose and meets the Australian weather challenges.
Risk mitigation strategies | Has all risk mitigation strategies been considered for the proposed surface, including:
i.Environmental aspects, ii.Community usage, iii.Economic considerations.
Technology usage | How can technology be used to assist with the management of the facility (e.g. Tennis Australia’s Book A Court platform, Lighting software, Intelligent Play etc).
Program needs & management | Does this new surface allow for greater programming and usage without detrimental impact on the surface.
Replacement strategy | Has a replacement strategy and funding fund been considered.
Environmental Considerations
Whole of parkland assessment | Exploration of a whole of parkland masterplan should be considered to ensure that any field of play design is aligned with the strategic needs of the site. Impact of the field of play for the whole site - including tree canopy, fauna, flora, water harvesting, parking, lights, etc).
Placement of field of play – to minimise the impact of the field on other environmentally or community-sensitive areas (e.g. waterways, bushfires, etc).
Climate change impact - has the design embraced the Australian Institute of Landscape Architects, Climate Positive Design (Vol 1-3) Guidance.
Tree planting – to reduce climate challenges and carbon sink and possible impacts to Urban Heat Island (UHI) impacts.
Active, Passive recreation impact – will the new facility have a significant impact on passive recreation in the area? Will it significantly impact the hours of play in a manner that will impact the local community.
Accessibility – Consider whether the new facility will impact people using the site, accessing the site and whether will it be perceived as being safe and accessible by all.
Civil engineering considerations | Site geotech report - to ascertain the ability of the site to accommodate the pavement base, and in what form to ensure that it can be built for a minimum of 20 years.
Site environment assessment – to consider all soil health issues.
Flood report – that may impact the site longevity and ability to construct as flooding needs strategic engineering solutions for certain types of flooding.
Site survey – to be able to design and build the site to its optimal performance.
Tree management report – in relation to any trees impacting the field of play and also how the tree canopy can be expanded with the careful planting of additional trees, for shade, reduce surface heat, and offset any UHI impact. Need to consider new legislation - Urban Forest Act 2023. Consider 30yr forecast of tree root system and branch overhang.
Review of the whole of site access – to ascertain pedestrian and vehicle travel around the site from the development and during the development, reducing the impact on the community.
Site overlays – has the site any overlays such as heritage importance, restrictive zoning, previous landfill, existing easements etc.
Pavement base - 20-year minimum design and preference is for 30 years to ensure that the investment can make a difference to generations of children and sports players
Geotech site assessment is needed to ascertain the ability of the site to accommodate the pavement base, and in what form to ensure that it can be built for a minimum of 20 and preferably 30 years.
Drainage strategy – to address a 1 in 20-year ARI event of approx 20 mins is allowed for and preferably 1 in 50-year ARI. It is important that the drainage can disperse the water after heavy rainfall and for the sport to resume within an acceptable period.
Water harvesting – where affordable should be considered to provide a benefit back to the whole parkland.
Planning approval | New facilities, where a Development Application is required, need to adhere to local council obligations including a range of statutory documents and additional reference documents (e.g. District and Zone policies, Technical Specifications, Design Guides, District Strategies).
Environmental standards and Strategies | Environmental strategies to consider may include open space and tree canopy strategies, urban heat island impact reduction strategies and circular economy policies to name but a few.
Environmental standards to be considered should include the mitigation of microplastics etc.

## Design
Sports Surface Component Considerations | Benchmarked Solution and Preferences | Self-assessment Result
2. DESIGN
Performance Standards for Surface
Sports performance levels/ standards | The surfaces should be designed according to the International Federation standards for community sport, namely: •Football – FIFA, Quality mark •Rugby Union – World Rugby, Regulation 22 •Rugby League – NRL, Community Standard •Australian Rules – AFL/CA Community Standard •Hockey – FIH Natural Standards •Athletics – World Athletics, Category 2 The International Federation surface standards are the starting point and additional performance standards are needed for Australia due to our intensity of use, the environmental conditions, and the community's concern about health and safety.
Size of playing area | Ensure that the field size is linked to the level of play that is going to be held on the field, as the difference for an aspirational-sized field may add a further 25% to the costs.
Surface design specified | Line Marking - The line marking should meet the appropriate sports standards (e.g. state, national sports organisation, and that of the International Federation) depending upon the jurisdiction.
System design – Yarn - Dual yarn of monofilament and fibrillated tape with additional durability testing (Lisport test 2012 – over 100,000 cycles) to allow it to stand up to the intensity of use in Australia. Reduce ball splash and migration of infill, more durable combination and reducing the maintenance needs. Also reduces the likely migration of infill outside of the field of play. The design of the Field of Play needs to be designed to achieve AS TR CEN 17519:2021 Surfaces for Sports Areas – Synthetic turf facilities – Guidance on how to minimise infill dispersion into the environment
System design – infill - Organic infill options with a preference for limited floating. Heat level of 1-2 on the FIFA scale as opposed to rubber was 2.5 to 3 (40% heat reduction).. It is environmentally positive as it removes the rubbers from the system and the possible migration from the field. It will reduce the heat impact significantly and positively impact the perceptions of the community. This will address the perceived issue with some of the community who fear the rubber may have negative health impacts – which although not proven at any level – will stop this narrative.
Shockpad - Every system should have a shockpad that meets the European standard (EN 15330-4 (2022) Surfaces for sports areas (Part 4) and has been tested to the Sports International Federation standard. The shockpad should have a manufacturer (not supplier) warranty of a minimum of 20 years and for a minimum of 60 hours and not the normal 40 hours per week that some offer. The environmental preference is for the shockpad to be constructed from recycled products.
Certification standards | Is certification needed by the sport for compliance (Rugby Union, AFL only), if not does the sport require it?
Additional considerations | Additional standards for porosity and U.V. durability should be considered at this stage.
Planet (Environmental) Standards
Open Space strategy / master planning | Has the sports surface been aligned and agreed within a whole of open space masterplan, so that the environmental benefits (e.g. water harvesting, tree canopy, Urban heat island impact) have been embraced.
Surface environmental standards | The following SMART standards should be embraced for environmental good practice: •Infill and yarn should be tested to AS/NZS 2111.18 (1997) AS/ISO 9239-1 Flammable / melting point is acceptable •The Heat Indices (FIFA Quality manual) should be within a 1-2 score •All drainage should be under the field of play and achieve the AS Standards for Mitigation of Microplastic’s •European REACH regulations, Annex. XVIII entry 50: 2021 if rubber infill used •EN71.1 Safety of Toys – part 3 Mitigation of Certain elements, table 2 – category III (Scraped off material) or US standard ASTM F3188-16 The carpet system needs to be tested for additional durability for Australia (FIFA 2012 Quality manual – Lisport test with a minimum of 100,000 cycles and the higher the better, with some systems now offering over 300,000 cycles.
Climate action design alignment with good practice | Has the design embraced the Australian Institute of Landscape Architects, Climate Positive Design (Vol 1-3) Guidance.
Civil engineering standards | Has the pavement design been designed for 20 – 30 years.
Drainage strategy | Has the drainage been designed to accommodate and Annual Rain Intensity (ARI) of at least 1 in 20 year plus event.
Water harvesting | Can your design embrace water harvesting to water the rest of the parkland.
Lighting strategy | What lighting do you need for the fields (e.g. 50/100l lux) and what Australian Standards are needed. The light system should be LED, and have smart technology that allows for various settings including ‘warmup/down’,
Training, and competition (Various levels) to optimize costs and performance needs The standards should be specified against the various Australian Standards and aligned with the various sports needs •AS 2560.1 Sports Lighting, Part 1: General Principles •AS 2560.2 Sports Lighting Part 2: Specific Applications AS/NZS 4282:2019 Control of obtrusive effects of outdoor lighting (general and specifically appendix C).
Fence / netting standards | Fencing and netting need to balance the role between safety (keeping the ball within the field of play and reducing the opportunity of interaction with spectators or passersby) and keeping spectators out of the field of play while balls are being used. Consider public access where required. (non-exclusive lease).
AS 1725.5 – 2010 (reconfirmed 2020) Chain link fabric fencing Sports ground fencing – general requirements
Higher fencing should be considered at key points around the field of play to reduce the ball entering roads, high-use pedestrian areas and to protect other buildings, etc
Maintenance and renovation | Has the maintenance and renovation program been aligned with the life of the surface, with clear roles and responsibilities defined.
People (Community) Standards
Durability / intensity standards | If the facility is being used over 40 hours per week additional intensity usage standards need to be designed in.
Parking and transport | Public transport should be considered for access to fields. If this is difficult then there should be adequate parking for peak times and turnover of participants etc Conversion of current facilities needs Ensure adequate parking is available Explore the ease of public transport Lighting in parking areas to ensure that there is safety of users
Access to site and around whole of parkland | Is there good paths around the parkland to key local areas, including parking, toilets and amenities.
The width of the paths should be sized to their usage, 2.5-3m in high use areas.
Way finding | Has the way finding signage been developed and tested on people.
Pedestrian and vehicle access | Access points need to be DDA compliant and on a level to the paths with NO step down.
Equipment standards | International and SSA Sports standards need to be embraced.
Goal posts should be procured as aligned with the Australian standards compliance obligations, AS4866.1: Playing Field Equipment – Soccer goals.
Identify the standard of play that the field is primarily used for (not the aspirational level) and align the size of posts (e.g. AFL, Rugby, etc) as the post heights differ between local, district, and state-level competition.
Accessibility for public casual Usage | How will the site be designed to allow access for casual usage, so fences/gates are open for public use.
Prosperity (Economic) Standards
Whole of life costings | Has whole of life costings been calculated in a manner that includes capital costs, maintenance/renovation and replacement costs at the end of life.
Warranty’s | The performance system should have a manufacturer (not a supplier) warranty of 8 years (min) against a minimum of 60 hours of usage per week for 50 weeks a year (3,000 hours per annum).
Operational budget expectations | Operational costs for management, maintenance, replacement of infills (synthetic grass or sand) and repainting should be considered.

## Procurement
Sports Surface Component Considerations | Benchmarked Solution and Preferences | Self-assessment Result
3. PROCUREMENT
Procurement Process
Transparent process | A procurement program is needed to ensure transparency and rigor to secure fit for the for-purpose field of play.
Council procurement program should be used where possible to ensure transparent and rigorous procurement protocols are followed.
Tendering suitability | The tenderer chosen must have experience in the construction of these standard fields and the surfaces must be certified and approved by the Sports International Federation.
Tenderers/suppliers of such sports surfaces must be a licensed or preferred provider of the International Federation or an Agent of such an organisation and can supply a sports system that has been tested and has been certified by them to meet the sports standards/requirements.
Procurement documentation | The common Design and Construct (D&C) procurement strategy is fraught with dangers and although may present as a cheaper option in the short term will be more costly in the whole of life of the field.
Choose either a Design Finalisation and Construct (DF&C) or a Detailed Design (DD) strategy.
Where possible utilise the Government's standard documentation specifically amended for this type of contract.
Specification development | The development of the specification needs to consider the performance surface that is fit for purpose, the construction process and standards, environmental expectations, timelines and details from the client side to ensure that the tenderers have a complete understanding of the site history, current condition and how it will be used.
It is imperative that the writer is knowledgeable of all standards and needs.
Encourage innovation in the system options to demonstrate best value for the community and user.
Evaluation strategy | The evaluation strategy should consider a weighted system that explores, the experience and capability of the tenderer, their capacity and availability for your timelines, the costs (whole of life recommended), the product you are purchasing and the methodology they will employ to construct and install it.
Procurement timetable | The procurement time lines need to explore the tendering timelines (4-5 weeks), the evaluation and decision-making process (4+ weeks), the negotiation period (2-4 weeks), the project management of the design finalisation, manufacturing process, construction, installation and certification process.
Certification standards | Certification to the International and ASC Sports standards once complete and ongoingly.
All sports fields need to be procured in a manner that ensures that the International Sports Federations’ performance standards are achieved as a minimum, plus Australian-specific needs as per the Design Guide (e.g. UV radiation, water porosity, etc).
Construction Project Management
Project Management | A detailed project plan and an identified project manager from both teams.
Ensure sufficient time is allowed for each stage, for wet days, and a contingency is built in.
A detailed project plan will bring together all parties and ensure an aligned timeline that reduces the probability of overrun and additional costs.
Quality Control | Assuring the quality is crucial throughout the project and once it has been installed.
There should be Critical Hold Dates that allow for independent assessment before the next stage continues, around project management, construction steps, and completion.
The field should be certified by an approved International Federation approved assessment company to ensure that the surface performs to the levels specified.
Handover
Formal handover process | There should be a default handover period, normally 12 months so if anything goes wrong then the tenderer corrects it at no cost to the sport or the purchaser.
Handover documentation
Defects liability period | This should be for 12 months and have an independent assessment at the end of that period to provide council with the confidence especially over the performance of the surface.

## Management
Sports Surface Component Considerations | Benchmarked Solution and Preferences | Self-assessment Result
4. MANAGEMENT
Facility Management
Management options | The management of the facility should be considered in a manner that allows the greatest number of people from across the community to utilise the asset and play sport. This should be documented and all partners agree the delivered outcomes.
Management options may be documented as lease agreements, licences to use, MoU’s etc.
Roles & responsibilities | There needs to be clarity of roles between all parties including management issues, cleaning & maintenance, programming, replacement funding, management of revenue and expenses, etc.
Maintenance
Roles & responsibilities | The maintenance of the surface is paramount to its performance, safety and life expectancy. The tasks needed for this should be clearly articulated and defined between ALL parties. These cannot be abdicated through a contract.
Routine maintenance | Routine maintenance, such as brushing is needed and should have shared responsibility between the Club and specialist machinery (e.g. Council and contractor).
Programmed maintenance | Programmed maintenance such as ‘Deep Cleans’ and infill replacement need to be allocated across the year so that they are completed at the correct parts to the season.
Seasonal renovations | Seasonal renovations should be planned to have pre or post season so that it impacts the players positively. This should include infill upgrades, deep water cleaning, line marking, etc.
Specialist work | Is there specialist work that needs to be identified that isn’t operationally completed on-site by the club or council? This is normally where specialist machinery is needed.
Older life maintenance | As the surface ages additional maintenance and repair work will be needed and this should both be programmed in to the maintenance/renovation calendar and economic resources allocated.
Repairs | Repairs will need to be accounted for, so a contingency operational budget should be allocated.
Annual review | An independent annual review should be developed to ensure that the life expectancy can be addressed.
Surface Programming
Routine programming | Programming of the field/surface should include working with other stakeholders, such as local schools and other sports to manage the assets.
Technology embracement | Technology for the lights, maintenance and program should be connected if it allows greater data to be collected and management decisions to be made. This could include use of intelligent play, booking systems, etc.
Measuring Impact
Demonstrating impact | To create a community impact focused on growing participation can be created by additional hours for children and adults to have access to more sports fields. Measuring this impact will quantify the effects that technology can have on actual participation.
KPI’s | Identify key measures to justify the impact that the new sports facility is having on the community by collecting the data that should include: •Club members – annual before and after •Usage – the number of hours per week/year •Usage – the number of players (adults/Children) •Hours of maintenance/hours of use ratio •Cost of maintenance per annum •Hectares of synthetic v natural turf fields in the municipality •Amount of water used before and after installation
Replacement Strategy
Replacement | The anticipated replacement date should be calculated annually to ensure that the field can achieve its life expectancy, which will be determined by the type and intensity of usage with the maintenance program to reduce the impact of the usage. From the annual review consider when the field of play needs to be replaced and ensure that there is a sinking fund in place to be able to afford its replacement.
Supporting infrastructure and equipment standards
Pathway standards | The width of the pathways should be a minimum of 1.8m and preferably 3m, linked to the expected number of spectators while still allowing 1.8m outside of the spectator’s ‘line.’